## EPICs
| EPIC Details |  |  |  | Projects | [10 empty] | O-RAN Workgroup Interests | [7 empty] | E2E Use Cases
ID | Title | IsBacklog | sub-project | Notes | INF | INT | RIC | RICAPP | NONRTRIC | OCU | OAM | SIM | ODUH | ODUL | ORU | WG1 | WG2 | WG3 | WG4 | WG5 | WG6 | WG7 | WG8 | HealthCheck | Column2
| [RIC-A-F10] Recovery after connection failure restoral | Y |  |  |  |  | Y | bar: O-RAN Workgroup Interests WG3
| [RIC-A-F11] Rainy Day Interface Handling | Y |  |  |  |  | Y | bar: O-RAN Workgroup Interests WG3
| [RIC-A-F13] Improve Component Implementation Performance | Y |  |  |  |  | Y | bar: O-RAN Workgroup Interests WG3
| [RIC-A-F14] Provide Platform Healthcheck | Y |  |  |  |  | Y | bar: O-RAN Workgroup Interests WG3
| [RIC-A-F18] Maintaining Message Routing after Recovery | Y |  |  |  |  | Y | bar: O-RAN Workgroup Interests WG3
| [RIC-A-F24] Restore Routing after Restart or Recovery | Y |  |  |  |  | Y | bar: O-RAN Workgroup Interests WG3
| [RICAPP-A-F60] Develop Test Strategy for an xAPP | Y | [5 empty] | Y | bar: O-RAN Workgroup Interests WG3
| [RICAPP-A-F100] Support xApp-generated alarms | Y | [5 empty] | Y | bar: O-RAN Workgroup Interests WG1
| [RICAPP-A-F010] Support xApp policy guidance using pre spec A1 messages | Y | [5 empty] | Y | bar: O-RAN Workgroup Interests WG2
| [RICAPP-A-F090] Support xApp API/RIC transaction tracing | Y | [5 empty] | Y | bar: O-RAN Workgroup Interests WG3
| [RICAPP-A-F004] ML Based Admission Control xApp | Y | [5 empty] | Y | bar: O-RAN Workgroup Interests WG2 to O-RAN Workgroup Interests WG3
| OTF Integration with LF CICD tool chain |  |  |  |  | Y
| OTF VTH for E2 SIM |  |  | If this is compliance to an OTF API then possibly this should be in the SIM Project | [7 empty] | Y | bar: O-RAN Workgroup Interests WG3
| OTF VTH for UE SIM |  |  | If this is compliance to an OTF API then possibly this should be in the SIM Project | [7 empty] | Y | bar: O-RAN Workgroup Interests WG4; O-RAN Workgroup Interests WG8
| Test spec for Open Front Haul |  |  |  |  | Y | bar: O-RAN Workgroup Interests WG4
| Use KPI xAPP Stubs to create E2 SIM capabilities for O-DU and O-CU-UP | [10 empty] | Y | bar: O-RAN Workgroup Interests WG3
| O1 interface simulator netopeer (open src netconf server) | [10 empty] | Y
| Use NETCONF for RIC CM | [5 empty] | Y | bar: O-RAN Workgroup Interests WG1; O-RAN Workgroup Interests WG3
| RIC adoption of O-RAN IM | [5 empty] | Y | bar: O-RAN Workgroup Interests WG1; O-RAN Workgroup Interests WG3
| A1 Mediator Enhancements for A1-P | [5 empty] | Y | bar: O-RAN Workgroup Interests WG2 to O-RAN Workgroup Interests WG3
| A1 Mediator Enhancements for A1-EI | [5 empty] | Y | bar: O-RAN Workgroup Interests WG2 to O-RAN Workgroup Interests WG3
| A1 Mediator Enhancements for A1-ML | [5 empty] | Y | bar: O-RAN Workgroup Interests WG2 to O-RAN Workgroup Interests WG3
| A1-P through SDN-R | [7 empty] | Y | bar: O-RAN Workgroup Interests WG2
| A1-P simulator ONAP testing |  |  |  |  | Y | [5 empty] | Y
| CM Notification (ORAN/ONAP) |  |  | Jensen | [6 empty] | Y
| Trace data collection, 3gpp, oran, onf |  |  | Jensen | [6 empty] | Y
| Near-RT RIC restart |  |  | svc mgmt, FCAPS is done by SMO | [6 empty] | Y
RICP1000 | Adapt to reverse E2 setup (if WG3 decides so) |  | E2 term, E2 manager | 0 |  |  | y | bar: O-RAN Workgroup Interests WG3
RICP1001 | Adapt to E2 message set that is not reusing X2 (if WG3 decides so) |  | E2 term, E2 manager |  |  |  | y | bar: O-RAN Workgroup Interests WG3
RICP1002 | DB HA integration |  | DB | pushed from R2 to R3 |  |  | y | bar: O-RAN Workgroup Interests WG3
RICP1003 | SDL-API version check against redis module (detect incompatibility) |  | DB |  |  |  | y | bar: O-RAN Workgroup Interests WG3
RICP1004 | DB Documentation & basic examples |  | DB |  |  |  | y | bar: O-RAN Workgroup Interests WG3
RICP1005 | DB Python API - native implementation |  | DB |  |  |  | y | bar: O-RAN Workgroup Interests WG3
RICP1006 | DB Findkeys support in KV API |  | DB |  |  |  | y | bar: O-RAN Workgroup Interests WG3
RICP1007 | DB Scaling (multiple independent redis-slave instances or cluster)' |  | DB |  |  |  | y | bar: O-RAN Workgroup Interests WG3
RICP1008 | Namespace management API: xAPP can register namespaces / xAPP Manager can clean on xAPP removal |  | DB | likely as REST API (plus library) |  |  | y | bar: O-RAN Workgroup Interests WG3
RICP1009 | DB C++, Go, Python API harmonization |  | DB |  |  |  | y | bar: O-RAN Workgroup Interests WG3
RICP1010 | DB Loadable LUA support for module implementations |  | DB | enables re-use of plain Redis |  |  | y | bar: O-RAN Workgroup Interests WG3
RICP1011 | Notification API for total DB reset (namespace is lost) |  | DB |  |  |  | y | bar: O-RAN Workgroup Interests WG3
RICP1012 | Security architecture POC (Redis6 offers both SSL/ACL support) |  | DB |  |  |  | y | bar: O-RAN Workgroup Interests WG3
RICP1013 | Automated FT cases for DB |  | DB |  |  |  | y | bar: O-RAN Workgroup Interests WG3
RICP1014 | Streaming: Versioning support |  | Message streaming |  |  |  | y | bar: O-RAN Workgroup Interests WG3
RICP1015 | Streaming: Testcases to verify messages compile and are usable |  | Message streaming |  |  |  | y | bar: O-RAN Workgroup Interests WG3
RICP1016 | Streaming: Documentation |  | Message streaming |  |  |  | y | bar: O-RAN Workgroup Interests WG3
RICP1017 | Streaming: Convert all octets strings to bytes |  | Message streaming |  |  |  | y | bar: O-RAN Workgroup Interests WG3
RICP1018 | Streaming: Technical study of generating protobuf definitions directly from ASN.1 |  | Message streaming |  |  |  | y | bar: O-RAN Workgroup Interests WG3
RICP1019 | RNIB: Use streaming protocol buffers in UENIB writer / reader |  | RNIB | since this is "only" documentation not sensible to work on |  |  | y | bar: O-RAN Workgroup Interests WG3
RICP1020 | RNIB: scaling (architecture, POC?) |  | DB |  |  |  | y | bar: O-RAN Workgroup Interests WG3
RICP1021 | YAML override |  | xApp manager (TODO-check) | left over from R2 |  |  | y | bar: O-RAN Workgroup Interests WG3
RICP1022 | set up open-src CI for RIC platform |  | CI |  |  |  | y | bar: O-RAN Workgroup Interests WG3
RICP1023 | xApp APIs (C++, Go) for subscription management that make xApps independent of ASN.1 |  | Subscription manager | Make xApps independent of E2 ASN.1. This would be, e.g., removal of SubscrptionRequest ASN.1-encocded RMR messages in the xApp interface. So that xApps only depend on the ASN.1 they actually understand. E.g. an S1 xApp only needs S1 ASN.1. Most likely this means Protobuf + Go/C++ library on top of that. E.g if E2SM uses only JSON encoding, then xApp must be implementable without ever touching an ASN1 compiler |  |  | y | bar: O-RAN Workgroup Interests WG3
RICP1024 | E2 Term and xApps to communicate via google proto buf - only the actual messages are encoded in whatever format the E2SM define |  | E2 term | TODO This might mean that we do not have message type based routing in RMR anymore? |  |  | y | bar: O-RAN Workgroup Interests WG3
RICP1025 | Subscription merging for single-action subscriptions, but not for multi-action subscriptions |  | Subscription manager | As per "RICsubscription procedure with merge" and "RICsubscriptionDelete procedure with merge" in the subscription manager software architecture |  |  | y | bar: O-RAN Workgroup Interests WG3
RICP1026 | Subscrption chaining. |  | Subscription manager |  |  |  | y | bar: O-RAN Workgroup Interests WG3
RICP1027 | Formal alarm handling from xApps and from RICplatform |  | Alarm manager |  |  |  | y | bar: O-RAN Workgroup Interests WG3
RICP1028 | A1 |  | A1 adapter |  |  |  | y | bar: O-RAN Workgroup Interests WG3
RICP1029 | O1 (outside of stats, CM, FM) |  | ? | TODO |  |  | y | bar: O-RAN Workgroup Interests WG3
RICP1030 | O1-CM (replacing ConfigMap) for xApps and for teh RIC platform, including MO (managed object) model. |  | CM |  |  |  | y | bar: O-RAN Workgroup Interests WG3
RICP1031 | Versioning and upgrade of xApps (incl. rolling upgrade, and subscription routing) |  | xApp manager, RMR |  |  |  | y | bar: O-RAN Workgroup Interests WG3
RICP1032 | scalability of xApps |  | ? | not in B release |  |  | y | bar: O-RAN Workgroup Interests WG3
RICP1033 | study item: RMR and other message bus (Kafka and NATS streaming) |  | RMR |  |  |  | y | bar: O-RAN Workgroup Interests WG3
RICP1034 | Subscriptions for parameter changes |  | Subscription manager | TODO-check-with Alistair if "policy" subscriptions actually expect any messages back (right now subscription type is not used for anything in subscription and all 3 types are handled the same). I am not sure if there's much sense in any subscription that only ask for parameter changes. I think it will mostly be (1) "one-of"/once subscriptions and (2) "current plus delta" subscriptions. Note that (1) has a problem that subscriptions could actually be torn down after the current value was delivered. Same situation in US#4. It seems that for such subscrptions as per (1) or per US#4 would not actually have indication messages. Should we have some optimization on RIC and enB side that releases subscription resources (e.g. in RIC subscription manager) once the subscription response has been deleivered? Or actually on RIC side we could even think about such messages being send without the subscription manager. |  |  | y | bar: O-RAN Workgroup Interests WG3
RICP1035 | RICP components to take tracing into use (all-in-one Jaeger is already available) |  | Tracing |  |  |  | y | bar: O-RAN Workgroup Interests WG3
RICP1036 | Tracing: Jaeger Collector container |  | Tracing | https://rancodev.atlassian.net/browse/RICPLT-1681 |  |  | y | bar: O-RAN Workgroup Interests WG3
RICP1037 | Tracing: Jaeger Agent in a side-car container |  | Tracing | https://rancodev.atlassian.net/browse/RICPLT-1680 |  |  | y | bar: O-RAN Workgroup Interests WG3
RICP1038 | Tracing: Support for "remote" sampling mode, enabling and disabling trace (stretch) |  | Tracing | https://rancodev.atlassian.net/browse/RICPLT-1682 |  |  | y | bar: O-RAN Workgroup Interests WG3
RICP1039 | actual metrics from platform components |  | Stats | Depends on RICP1040 |  |  | y | bar: O-RAN Workgroup Interests WG3
RICP1040 | VESPA Manager starts up VESPA with RIC Platform component metrics data received via init |  | Stats |  |  |  | y | bar: O-RAN Workgroup Interests WG3
RICP1041 | Routing Manager: Support for merged subscriptions |  | Routing manager, RMR |  |  |  | y | bar: O-RAN Workgroup Interests WG3
RICP1042 | Routing Manager: Support for xApp chaining |  | Routing manager |  |  |  | y | bar: O-RAN Workgroup Interests WG3
RICP1043 | Routing Manager: HA (restart), but no redundancy |  | Routing manager |  |  |  | y | bar: O-RAN Workgroup Interests WG3
RICP1044 | Routing Manager: use incremental updates for routing table in RMR |  | Routing manager | requires RICP1045 first |  |  | y | bar: O-RAN Workgroup Interests WG3
RICP1045 | Routing Manager: only query routes from xApps that have been added/deleted, but not from all everytime an xApp has been added/deleted |  | Routing manager |  |  |  | y | bar: O-RAN Workgroup Interests WG3
RICP1046 | Routing Manager: re-use generic libraries from xApp framework or full framework |  | Routing manager | Note subscription manager is already xApp framework based |  |  | y | bar: O-RAN Workgroup Interests WG3
RICP1047 | Routing Manager: replace use of Go's mangos implementation to use C implementation of RMR in go. |  | Routing manager | Routing manager only uses RMR's management interface |  |  | y | bar: O-RAN Workgroup Interests WG3
RICP1048 | RoutingManager: use RIC tracing |  | Routing manager |  |  |  | y | bar: O-RAN Workgroup Interests WG3
RICP1049 | RoutingManager: better debugging capabilities |  | Routing manager | e.g. dumping current routing tables |  |  | y | bar: O-RAN Workgroup Interests WG3
RICP1050 | Subscription manager: Better debugging capabilities |  | Subscription manager | e.g., dumping subscriptions (alternatively do this via "Subscription API for operators and other RIC components.") |  |  | y | bar: O-RAN Workgroup Interests WG3
RICP1051 | Test cases added to asn1c for the fixes/changes that we did |  | asn1c | e.g. 64 bit support |  |  | y | bar: O-RAN Workgroup Interests WG3
RICP1052 | Upstreaming asn1c changes to Lev Walkin's branch |  | asn1c | this way we don't have to maintain a fork anymore. |  |  | y | bar: O-RAN Workgroup Interests WG3
RICP1053 | Subscription manager: Timer support |  | Subscription manager | Submgr would support TRICEVENTcreate and TRICEVENTdelete timers, as defined in the E2AP Specification. |  |  | y | bar: O-RAN Workgroup Interests WG3
RICP1054 | Subscription manager: Rainy day scenario support |  | Subscription manager | Submgr would support different rainy day scenarios, that could occur during operation. Such rainy day scenarios could be: Message collision: Two request messages request action on the same subscription at the same time. Failure in gNb: Failure message received from gNb, Late messages: Messages received after timer expiration , Rtmgr failure during initial subscription, merge, delete or delete merge scenario, Message duplication at any stage of any scenario, Faulty messages - payload-wise: The message cannot be decoded, Faulty messages - value-wise: The message contains non-valid information, such as non-exitent RICsubscriptionID. There are additional failure scenarios in an internal document attached to ".../Feature+candidates" |  |  | y | bar: O-RAN Workgroup Interests WG3
RICP1055 | Subscription manager: Application chaining (for "insert" subscriptions) |  | Subscription manager | Sumbgr would support application chaining, i.e. being capable to handle RICsubscriptionRequest messages that are identical in terms of the subject of subscription, but contain RICactionType set to insert. Note: This feature requires RIC level design. |  |  | y | bar: O-RAN Workgroup Interests WG3
RICP1056 | Subscription manager: Multiple RICactions-ToBeSetup-List members |  | Subscription manager | Submgr would support RICsubscriptionRequest messages with RICactions-ToBeSetup-List IE's that contain more than one RICaction-ToBeSetup-Item IE. Note: This feature requires RIC level design. |  |  | y | bar: O-RAN Workgroup Interests WG3
RICP1057 | Subscription manager: High availability (restart, but no redundancy), including state in DB |  | Subscription manager | Submgr would support high availabilty features that enable the application to provide services during or after different failures. Such scenarous could be: Submgr restart, Rtmgr restart, Temporary connection failure One enabler of high availability could be the session state externalization. In case of Submgr the two main data structures that represent the application's state are transaction_table and the subscription_table. |  |  | y | bar: O-RAN Workgroup Interests WG3
RICP1058 | Subscription manager: Tracing |  | Subscription manager |  |  |  | y | bar: O-RAN Workgroup Interests WG3
RICP1059 | Subscription manager: Logging |  | Subscription manager |  |  |  | y | bar: O-RAN Workgroup Interests WG3
RICP1060 | Subscription manager: Subscription API for operators and other RIC components. |  | Subscription manager | Submgr would provide an API to let other RIC or RIC Platform components to retrieve information about the subscriptions. Such API could be HTTP-based, following the RESTful principles. |  |  | y | bar: O-RAN Workgroup Interests WG3
| O-RAN Specification to support Dynamic Data Collection (DDC) Activation and Deactivation |  |  | As a user of network element (NE) data, I want to be able to use O-RAN interfaces to support Dynamic Data Collection (DDC) Activation and Deactivation | bar: O-RAN Workgroup Interests WG1 to O-RAN Workgroup Interests WG8
| O-RAN Specification to support Dynamic Data Collection (DDC) Measurement Intervals |  |  | As a user of network element (NE) data, I want to be able to use O-RAN interfaces to set Dynamic Data Collection (DDC) Measurement Intervals. | bar: O-RAN Workgroup Interests WG1 to O-RAN Workgroup Interests WG8
| O-RAN Specification to support Dynamic Data Collection (DDC) Collection Intervals |  |  | As a user of network element (NE) data, I want to be able to use O-RAN interfaces to set Dynamic Data Collection (DDC) Collection Intervals. | bar: O-RAN Workgroup Interests WG1 to O-RAN Workgroup Interests WG8
| API to support Dynamic Data Collection (DDC) Measurement Intervals |  |  | API to support Dynamic Data Collection (DDC) Measurement Intervals |  |  |  |  | y | bar: O-RAN Workgroup Interests WG1 to O-RAN Workgroup Interests WG8
| RAN NE to support Dynamic Data Collection (DDC) Measurement Intervals |  |  | RAN NE to support Dynamic Data Collection (DDC) Measurement Intervals |  |  | y |  |  | y |  |  | y | y | bar: O-RAN Workgroup Interests WG1 to O-RAN Workgroup Interests WG8
| CLI to support Dynamic Data Collection (DDC) Measurement Intervals |  |  | As an administrator or provileged user of network element (NE) data, I want to be able to have a CLI support Dynamic Data Collection (Dynamic Data Collection (DDC)) Measurement Intervals. |  |  |  |  | y | bar: O-RAN Workgroup Interests WG1 to O-RAN Workgroup Interests WG8
RICP1061 | Scalability support with assumption that E2M handles the E2-node to E2T mapping. |  | Routing manager | bar: O-RAN Workgroup Interests WG1 to O-RAN Workgroup Interests WG8
RICP1062 | Configurable platform routes (now hardcoded) |  | Routing manager | more details needed |  |  | y | bar: O-RAN Workgroup Interests WG1 to O-RAN Workgroup Interests WG8
RICP1063 | RICP Documentation in wiki or as markup in the component |  | all | generally documentation for RICP is in wiki page or in a RICP component. If RIC component we apply the structure outlined in this e-mail thread: https://lists.o-ran-sc.org/g/main/topic/34173753#276. Documentation outside of RICP is not falling under this item. |  |  | y | bar: O-RAN Workgroup Interests WG1 to O-RAN Workgroup Interests WG8
RICP1064 | Multiple containers in same pod |  | Integration | (e.g. in ML needed). Presumable there are issues in this with the helm chart generation (for xApps) we have in integration code. |  |  | y | bar: O-RAN Workgroup Interests WG1 to O-RAN Workgroup Interests WG8
RICP1065 | documentation on one-step RIC platform and how to develop an xApp |  | xApp Framework | multiple requests received for this.
RICP1066 | Support for MEID (managed element) in subcription manager |  |  | Submgr would support the meid parameter, i.e. the Managed Element ID. By supporting the meid parameter, that is received via the RMr header, Submgr would be able to handle subscriptions that are located in different RAN elements, i.e in different gNb or eNb elements. |  |  | y | bar: O-RAN Workgroup Interests WG1 to O-RAN Workgroup Interests WG8
| Provide E2E Healthcheck Test |  |  | Test O1 User Story Test Alarm Test PM Test Heartbeat Test E2 Test A1 User Story |  | Y | [17 empty] | Y | bar: O-RAN Workgroup Interests WG1 to O-RAN Workgroup Interests WG8
| Support A1 Policy Test Message Generation | [7 empty] | Y | [14 empty] | Y | bar: O-RAN Workgroup Interests WG1 to O-RAN Workgroup Interests WG8
| Support A1 Policy Test Message Mediation | [5 empty] | Y | [16 empty] | Y | bar: O-RAN Workgroup Interests WG1 to O-RAN Workgroup Interests WG3
| Support O1 Healthcheck Provisioning Command |  |  | Support E2 Test Message User Story Support O1 Test Alarm User Story Support O1 Test Hearbeat User Story Support O1 Test Performance (HealthCheck Summary) Report User Story |  |  | Y | [16 empty] | Y | bar: O-RAN Workgroup Interests WG1 to O-RAN Workgroup Interests WG3
| Support A1 Policy Test Message Processing | [6 empty] | Y | [15 empty] | Y | bar: O-RAN Workgroup Interests WG1 to O-RAN Workgroup Interests WG3
| Support E2 Test Message Processing | [10 empty] | Y | [11 empty] | Y | bar: O-RAN Workgroup Interests WG1 to O-RAN Workgroup Interests WG3
| Support HealthCheck Telemetry (FM, Heartbeat, PM) | [9 empty] | Y | [12 empty] | Y | bar: O-RAN Workgroup Interests WG1 to O-RAN Workgroup Interests WG8
Note on Q20: KINSEY, DAVID F:

## OLD
Release B Epics
Near-RT RIC Project |  |  | RIC xApps |  | INT&TEST |  | Simulator |  | A1 | O1
[9 empty] | A1 northbound NONRTRIC (non-dashboard) | SDN-R using netconf
Title | [RIC-A-F10] Recovery after connection failure restoral | A1 mediator refinements | Title | [RICAPP-A-F60] Develop Test Strategy for an xAPP | Title | OTF Integration with LF CICD tool chain | Title | Use KPI xAPP Stubs to create E2 SIM capabilities for O-DU and O-CU-UP | A1-P refinements (REST) | s/w upgrade for m-plane specification (change mgmt)
[9 empty] | A1-EI (TBD, REST?, streaming interface) | PNF plug and play service (incorporates O1 information elements from WG1 InfoModel subteam)
Title | [RIC-A-F11] Rainy Day Interface Handling |  | Title | [RICAPP-A-F100] Support xApp-generated alarms | Title | OTF VTH for E2 SIM | Title | O1 interface simulator netopeer (open src netconf server)
Routing Mgr
Title | [RIC-A-F13] Improve Component Implementation Performance |  | Title | [RICAPP-A-F010] Support xApp policy guidance using pre spec A1 messages | Title | OTF VTH for UE SIM |  |  | Xapp Mgr
Title | [RIC-A-F14] Provide Platform Healthcheck |  | Title | [RICAPP-A-F090] Support xApp API/RIC transaction tracing | Title | Test spec for Open Front Haul
Title | [RIC-A-F18] Maintaining Message Routing after Recovery |  | Title | [RICAPP-A-F004] ML Based Admission Control xApp
Title | [RIC-A-F22] Persist Routing for Recovery/Restart
Title | [RIC-A-F24] Restore Routing after Restart or Recovery
high Availability
Scalability